## 工作表1
Task | Start Date | Days to complete | End Date
Find the website for API | 2019-12-17 | 3 | 2019-12-20
Obtain the API keys | 2019-12-20 | 3 | 2019-12-23
Analyze the data obtained from Spotify | 2019-12-23 | 5 | 2019-12-28 | 43478
Web crawl the IP of users | 2019-12-28 | 5 | 2019-01-02
Combine IP with Google Map | 2020-01-02 | 3 | 2019-01-05
Combine Spotify with Google Map | 2020-01-05 | 4
Finish | 2020-01-09 | 4

## 工作表2
Task | Start Date | Days to complete
get data from Spotify API | 2019-12-31 | 4
analyze the type of album | 2020-01-04 | 4 | 43830
point out the location using Google Map API | 2020-01-08 | 3
combine the list and the location on Google Map | 2020-01-11 | 2